## Blad1
|  |  | Ravan | Daan | Danny | David | Elio | Laura | Marc | Niels | Goal | Avarage time
ma | 2020-11-09 | 12:00 - 13:15 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | General consultation
wo | 2020-11-11 | 11:00 - 12:00 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | General consultation
vr | 2020-11-13 | 10:00 - 11:00 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | General consultation
|  | 12:00 - 19:00 | Marc: 5; Goal: Design concept 0.1
Total week 1 | Week 1 | Total | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 8.25 | 3.25 |  | 3.875
ma | 2020-11-16 | 09:00 - 10:30 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | General consultation + division of labor (sprint meeting)
|  | 10:30 - 12:30 | Laura: 2; Marc: 3; Goal: User Interface
|  | 11:30 - 15:00 | Ravan: 3; Goal: A&D problem description
wo | 2020-11-18 | 11:00 - 13:20 | Marc: 2.5; Niels: 2.5; Goal: Flow Chart user interface
|  | 14:00 - 16:00 | David: 2; Marc: 2.5; Goal: Analysis document
do | 2020-11-19 | 11:00 - 14:00 | David: 3; Elio: 3; Goal: Finish Analysis document
|  | 17:00 - 18:00 | Elio: 1; Goal: Finish Analysis document
vr | 2020-11-20 | 10:00 - 10:30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | End of the week meeting
|  | 10:30 - 16:30 | Laura: 6; Goal: Slides build.basic, build.roads, build.signs, build.building.build.lights, simulator.basic simulator.weather, simulator.driver, simulator.vehicle.
|  | 12:00 - 13:00 | Elio: 1; Goal: Finish How To document
|  |  | 0.5 |  |  | 0.5 |  |  |  |  | A&D final check
zo | 2020-11-22 | 11:00 - 15:00 | Ravan: 3; Goal: Powerpoint
Total week 2 |  |  | 8.5 | 2 | 2 | 7.5 | 7 | 10 | 10 | 4.5 |  | 6.4375
ma | 2020-11-23 | 09:00 - 10:00 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Sprint Meeting
|  | 18:00 - 19:00 | Daan: 1; Goal: Preparing presentation
[5 empty] | 8 |  |  | 8 |  |  | Video
|  | 13:00 - 17:00 | Marc: 5; Goal: User Interface
di | 2020-11-24 | 10:00 - 13:00 | Marc: 4; Niels: 3; Goal: User Interface
|  | 14:00 - 18:00 | Marc: 5; Niels: 4; Goal: User Interface
|  | 19:30 - 20:30 | Daan: 1; Goal: Preparing
wo | 2020-11-25 | 09:00 - 13:30 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | Presentation
[5 empty] | 3 |  | 3 | 3 |  |  | Cars
do | 2020-11-26 | 11:00 - 12:00 | Marc: 3; Niels: 1; Goal: User Interface
|  | 12:00 - 15:00 | Ravan: 3; Daan: 1; David: 3; Goal: Roads
vr | 2020-11-27 |  | Danny: 3; Elio: 4; Laura: 4; Goal: Cars
|  | 11:30 - 14:30 | Ravan: 3; David: 3; Goal: Roads
|  | 18:00 - 23:00 | Marc: 4; Niels: 5; Goal: User Interface
zo | 2020-11-29 | 12:30 - 13:30 | Ravan: 1; Daan: 1; David: 1; Goal: Grid
Total week 3 |  |  | 12.5 | 9.5 | 19.5 | 12.5 | 12.5 | 20.5 | 26.5 | 18.5 |  | 16.5
ma | 2020-11-30 | 09:00 - 09:30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Sprint Meeting
|  | 10:00 - 11:00 | David: 1; Laura: 1; Goal: Json for Vehicles
dins | 2020-12-01 | 09:15 - 12:15 | Danny: 3; Marc: 4; Goal: Interface
wo | 2020-12-02 | 11:00 - 14:30 | Ravan: 3.5; Elio: 1; Laura: 3.5; Goal: AI start
vr | 2020-12-04 | 10:00 - 11:00 | Laura: 1; Goal: Standard vehicles Json
|  | 10:00 - 12:30 | Daan: 2.5; Danny: 3; Marc: 5; Goal: Grid met UserInterface
|  | 12:30 - 15:30 | Ravan: 3; Elio: 3; Laura: 3; Goal: AI performance & multiple cars
za | 2020-12-05 | 12:30 - 15:30 | Ravan: 3; Niels: 3; Goal: Roads
| 2020-12-06 | 10:00 - 14:00 | Marc: 4; Goal: User interface
Total week 4 |  |  | 10 | 3 | 6.5 | 1.5 | 4.5 | 9 | 13.5 | 3.5 |  | 6.4375
ma | 2020-12-07 | 09:00 - 12:30 | 0.5 | 0.5 | 3.5 | 0.5 | 0.5 | 0.5 | 3.5 | 3.5 | Sprint Meeting + User Interface
|  | 12:00 - 13:30 | Ravan: 1.5; David: 1.5; Elio: 1.5; Marc: 2; Goal: Samenvoegen begin
di | 2020-12-08 | 09:00 - 12:00 | Danny: 3; Niels: 3; Goal: Midterm report + User Interface
|  | 15:00 - 16:30 | Ravan: 1.5; David: 1.5; Elio: 1.5; Marc: 2; Goal: Samenvoegen
|  | 16:30 - 18:00 | Marc: 3; Niels: 1.5; Goal: User Interface
|  | 17:00 - 19:00 | Laura: 2; Goal: Midterm Report Cars&Vehicles
wo | 2020-12-09 | 09:45 - 10:15 | Laura: 0.5; Goal: Midterm Report Cars &Vehicles
|  | 11:00 - 11:30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Sprint Meeting
|  | 11:30 - 13:30 | Niels: 2; Goal: User Interface
|  | 11:45 - 13:15 | Ravan: 1.5; David: 1.5; Goal: Multilane Roads
|  | 11:45 - 14:15 | Laura: 2.5; Goal: Midterm Report Roads
vr | 2020-12-11 | 11:30 - 12:30 | Daan: 1; Goal: Reading through/Correcting Midterm Report in anticipation of the Roadmap
|  | 10:00 - 16:30 | Ravan: 3; Elio: 6.5; Laura: 6.5; Goal: Vehicles accelerating/braking
|  | 10:00 - 11:00 | Ravan: 1; David: 1; Goal: Explanation comments Grid/Roads
|  | 15:00 - 16:00 | Daan: 1; Goal: Reading through/Correcting Midterm Report + Outline of the Roadmap
|  | 16:30 - 17:30 | Daan: 1; Goal: Expanding the Roadmap with relevant information like what needs to be done before we can replicate a scenario
|  | 16:30 - 17:30 | Ravan: 1; Goal: Explanation comments all classes
|  | 18:00 - 21:00 | Niels: 3; Goal: User Interface
|  | 20:00 - 21:00 | Elio: 1; Goal: Explaining/Discussing the projects for the first code review
Total week 5 |  |  | 10.5 | 4 | 7 | 6.5 | 11.5 | 12.5 | 11 | 13.5 |  | 9.5625
ma | 2020-12-14 | 11:00 - 11:30 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | Sprint meeting
|  | 15:00 - 17:00 | Marc: 3; Goal: Road designing
|  | 15:00 - 17:30 | Laura: 2.5; Goal: Vehicle single threaded
di | 2020-12-15 | 13:30 - 20:30 | David: 3; Elio: 4.5; Laura: 6.75; Goal: Working program for presentations
|  | 20:00 -23:00 | Daan: 3; Goal: Preparing the presentation/making slides
wo | 2020-12-16 | 09:30 - 10:30 | Elio: 1; Goal: New UI for prototype presentation
| 2020-12-16 | 09:00 - 12:30 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | Presentations
|  | 13:30 - 14:00 | 0.5 | 0.5 | 0.5 |  | 0.5 |  | 0.5 | 0.5 | Sprint meeting
do |  | 13:30 - 16:30 | David: 3; Laura: 3; Goal: UserInterface & Grid Controllers
vr | 2020-12-17 | 13:30 - 16:00 | 2.5 |  | 2 | 2 |  |  | 2.5 | 2.5 | Code Review
|  | 21:30 - 23:30 | Daan: 2; Goal: Combining Code Review
| 2020-12-18 | 10:00 - 10:30 | Ravan: 0.5; Daan: 0.5; Laura: 0.5; Niels: 0.5; Goal: Sprint meeting
za | 2020-02-19 | 10:30 - 13:45 | David: 3.25; Laura: 3.25; Goal: RoadController, SimulationScreenControllers and FlowCharts
Total week 6 |  |  | 7.5 | 10 | 6.5 | 14.75 | 10 | 20 | 10 | 7.5 |  | 10.7812
ma | 2020-12-21 | 11:00 - 11:30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Sprint meeting
|  | 11:30 - 12:45 | David: 1.25; Laura: 1.25; Goal: UI Json
|  | 11:30 - 13:30 | Ravan: 2; Daan: 2; Niels: 2; Goal: Roads richting
|  | 15:00 - 17:00 | Elio: 2; Marc: 2; Goal: Framebuffer
di | 2020-12-22 | 13:00 - 15:00 | David: 2; Laura: 2; Goal: UI Json
|  | 13:00 - 16:00 | Ravan: 2; Daan: 3; Danny: 2; Niels: 3; Goal: Roads richting/lanes/design
wo | 2020-12-23 | 11:00 - 14:00 | Daan: 3; Laura: 3; Goal: Merging Vehicle, Interface Update and Controllers to main + bug fixes
|  | 11:00 - 15:30 | Ravan: 4; Danny: 2; Niels: 4; Goal: Roads design
|  | 13:00 - 16:00 | Danny: 3; Marc: 3; Goal: Grid toggle
za | 2020-12-26 | 13:00 - 16:00 | Elio: 3; Marc: 3; Goal: framebuffer
zo | 2020-12-27 | 13:00 - 17:00 | Marc: 4; Goal: Grid
ma | 2020-12-28 | 10:30 - 11:00 | Daan: 0.5; Goal: Code review
|  | 11:00 - 11:15 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 | Sprint meeting
|  | 13:00 - 14:00 | David: 1; Laura: 1; Goal: Json Fix with main
di | 2020-12-29 | 13:00 - 16:00 | Ravan: 3; Danny: 3; Niels: 3; Goal: DiagonalRoads design
|  | 14:30 - 16:30 | David: 2; Laura: 2; Goal: Fix UserInterface + VehicleController
wo | 2020-12-30 | 11:00 - 11:15 | Ravan: 0.25; Daan: 0.25; Laura: 0.25; Niels: 0.25; Goal: Sprint meeting
|  | 12:00 - 12:30 | Daan: 0.5; Laura: 0.5; Goal: Vehicles
|  | 14:00 - 16:00 | Daan: 2; Laura: 2; Goal: Update Json UserControls
|  | 14:00 - 17:00 | Ravan: 3; Danny: 3; Niels: 3; Goal: CurvedRoad design
|  | 18:00 - 19:00 | Laura: 1; Goal: AiControllerbase & drivertypes
|  | 20:00 - 22:30 | Elio: 2.5; Laura: 2.5; Goal: Framebuffer
ma | 2021-01-04 | 11:00 - 11:30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | Sprint meeting
|  | 11:30 - 12:30 | Niels: 1; Goal: Simulation Timer fixed
|  | 11:30 - 15:30 | David: 4; Laura: 4; Goal: Vehicle en AI aan kunnen maken / Sign Start / maxSpeed Sign base
|  | 15:30 - 16:00 | Laura: 0.5; Goal: Next Steps document
|  | 14:00 - 16:30 | Daan: 2.5; Elio: 2.5; Goal: Origin points for spawning vehicles
|  | 20:30 - 23:15 | Laura: 2.75; Goal: Stop, Yield & PrioritySign base
di | 2021-01-05 | 11:00 - 15:00 | Ravan: 4; Danny: 4; Niels: 4; Goal: Road Connections
|  | 11:30 - 18:15 | David: 6.75; Laura: 6.75; Goal: Signs / Hitboxes
wo | 2021-01-06 | 11:00 - 11:15 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 | Sprint meeting
|  | 11:30 - 17:00 | Ravan: 5.5; Danny: 5.5; Niels: 5.5; Goal: DiagonalRoad fixed & Road Connections
|  | 11:15 - 19:45 | David: 8.5; Laura: 8.5; Goal: RectHitbox correctie + CurvedHitBox start
do | 2021-01-07 | 10:30 - 13:30 | Ravan: 3; Niels: 3; Goal: Road Connections
vr | 2021-01-08 | 09:00 - 10:00 | Elio: 1; Goal: Fixed framebuffer for multiple vehicles
|  | 10:00 - 10:15 | 0.25 | 0.25 |  |  | 0.25 | 0.25 | 0.25 | 0.25
|  | 10:15 - 13:45 | Daan: 2.5; Elio: 3.5; Goal: Randomized selection with weights for originpoints
|  | 10:15 - 16:15 | David: 6; Laura: 5; Goal: HitboxFix, HitBox test fix, driving direction arrow start, Popup Road start
Total kerst |  |  | 28.5 | 18 | 24 | 33 | 16.25 | 44.75 | 12.75 | 30.5 |  | 25.9688
ma | 2021-01-11 | 11:00 - 11:30 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | Sprint meeting
|  | 11:30 - 20:00 | David: 8.5; Laura: 8.5; Goal: Road Pop-up driving direction changable
di | 2021-01-12 | 10:00 - 12:45 | Ravan: 2.75; Danny: 2.75; Niels: 2.75
|  | 11:00 - 14:00 | Marc: 6
|  | 12:00 - 15:00 | Laura: 3; Goal: Curveflipping
|  | 15:00 - 19:00 | David: 4; Laura: 4; Goal: Driving direction flip & hitbox bugfix
wo | 2021-01-13 | 10:30 - 11:00 | Daan: 0.5; Goal: Code prereview
|  | 10:00 - 11:00 | Laura: 1; Goal: Hollow and convex curved road code
|  | 11:00 - 11:15 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 | sprint meeting
|  | 11:15 - 11:45 | Laura: 0.5; Goal: Hollow and convex curved road button (Temporary)
|  | 11:15 - 18:00 | Elio: 6.75; Goal: Mergen FrameBuffer + OriginPoints en OriginPoints afmaken + tekenen auto's
|  | 15:15 - 16:00 | Daan: 0.75; Goal: Code prereview
|  | 13:00 - 18:00 | Ravan: 5; Danny: 5; Niels: 5; Goal: Roads design
|  | 11:45 - 18:30 | David: 6.75; Laura: 6.75; Goal: Crossroads
do | 2021-01-14 | 10:00 - 13:00 | Ravan: 3; Niels: 3; Goal: Roads design
|  | 14:00 - 18:00 | Marc: 4; Niels: 4; Goal: Curved Road connection
|  | 13:00 - 15:00 | David: 2; Goal: Coding convention written
|  | 18:45 - 20:45 | David: 2; Goal: Adding comments and cleaning up code
|  | 20:00 - 21:00 | Elio: 1; Goal: Drawing cars on simulation screen
|  | 19:30 - 21:30 | Niels: 2; Goal: Finishing Curved Road design
vr | 2021-01-15 | 10:00 - 10:30 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Meeting with coach
|  | 10:15 - 11:00 | Laura: 0.75; Goal: Comments on roads and roadcontrollers
|  | 10:15 - 12:00 | Daan: 1.75; Goal: Reading Documention + fixing spelling mistakes
|  | 11:00 - 13:00 | David: 2; Laura: 2; Goal: Crossroads
|  | 13:00 - 15:15 | David: 2.25; Goal: Vehicles
|  | 10:15 - 15:30 | Elio: 5.25; Goal: Working on drawing vehicles + Fix acceleration and braking
|  | 15:15 - 18:30 | David: 3.25; Laura: 3.75; Goal: Working on vehicles and merging / finishing crossroad
|  | 10:30 - 18:00 | Danny: 7.5; Niels: 7.5; Goal: Curved and diagonal connection + user interface and traffic lights
|  | 18:30 - 22:00 | Niels: 3.5; Goal: Fixed minor bugs in connection and merged Visual_roads_2 in main
|  | 20:15 - 21:15 | Daan: 1; Goal: Adding comments and reading up on json in preparation for the saving/loading of projects
za | 2021-01-16 | 12:40 - 16:40 | David: 4; Goal: Made it so vehicles can drive on points
|  | 18:00 - 19:30 | David: 1.5; Goal: Allowed cars to switch from lanes
zo | 2021-01-17 | 11:30 - 12:30 | bar: Laura
|  | 13:30 - 16:00 | David: 2.5; Laura: 2.5; Goal: When switching from lanes = check if its possible
|  | 23:30 - 01:00 | David: 1.5; Goal: Write document for stuff for meeting
Total week 7 |  |  | 11.5 | 5.25 | 16.5 | 41.5 | 13.75 | 35 | 11 | 29 |  | 20.4375
ma | 2021-01-18 | 11:00 - 11:30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Sprint meeting
|  | 11:45 - 17:30 | David: 5.75; Laura: 5.75; Goal: Crossroad rules for vehicles
|  | 12:00 - 16:00 | Marc: 4; Goal: promotional material
|  | 12:00 - 18:15 | Daan: 6.25; Elio: 6.25; Goal: OriginPoints/ConnectionPoints + GPS
|  | 13:30 - 15:00 | Ravan: 1.5; Goal: Save/Load start & Crossroad connection start
di | 2021-01-19 | 09:00 - 11:00 | Daan: 2; Elio: 2; Goal: Json for OriginPoints/Dijkstra's algorithm
|  | 11:00 - 13:00 | Ravan: 2; Niels: 2; Goal: Save/Load
|  | 11:00 - 13:00 | Marc: 2; Goal: Promotional material
|  | 15:00 - 18:00 | Daan: 3; Elio: 3; Goal: IsConnection OriginPoints/Roads, Lanes & OriginPoints ophalen in de GPS
|  | 15:00 - 18:30 | Ravan: 3.5; Niels: 3.5; Goal: Save/Load
|  | 13:00 - 19:15 | Laura: 6.25; Goal: Json for RoadController, various bug-fixes, bit of help with GPSstart, and bug report filed
|  | 18:00 - 19:00 | Danny: 1; Goal: Hitbox Overlap
|  | 19:30 - 21:30 | Niels: 2; Goal: Saving recent projects to folder
wo | 2021-01-20 | 11:00 - 11:15 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | Sprint meeting
|  | 11:15 - 12:30 | Ravan: 1.25; Niels: 1.25; Goal: Save/Load preview picture
|  | 12:00 - 12:30 | Danny: 0.5; David: 0.5; Laura: 0.5; Goal: Hitbox overlap overleg
|  | 13:00 - 18:00 | Ravan: 5; Niels: 5; Goal: AutoSave & preview picture
|  | 12:00 - 18:15 | Daan: 6.25; Elio: 6.25; Goal: Dijkstra's algorithm + route + fix OriginPoints horizontale roads
|  | 12:30 - 18:30 | David: 6; Laura: 6; Goal: Vehicle priority rules, angle fixes
|  | 14:00 - 16:00 | Danny: 2; Goal: Overlap Hitbox
|  | 11:30 - 15:30 | Ravan: 3; Niels: 3; Goal: CrossRoad connection & save/load
do | 2021-01-21 | 12:00 - 14:00 | Marc: 2; Goal: Promotional material
|  | 13:30 - 16:00 | Ravan: 2.5; Niels: 2.5; Goal: cross connection
|  | 15:30 - 17:30 | Danny: 2; Elio: 2; Marc: 2.5; Goal: Code Review 2
|  | 13:00 - 20:30 | David: 7.5; Goal: Data collection/ World Config Creation // small bit for logic about crossroad
|  | 20:30 - 21:30 | Daan: 1; Goal: Research if A* is right for us (no, it's not) & reading BetterVehicle/AI for creation of GPS() tomorrow
vr | 2021-01-22 | 10:00 - 10:30 | 0.25 | 0.5 | 0.5 | 0.5 | 0.25 | 0.5 |  | 0.5 | Sprint meeting
|  | 10:30 - 12:00 | Laura: 1.5; Goal: Hitbox overlap fix and better collide method
|  | 10:00 - 12:30 | Daan: 2.5; Elio: 2.5; Goal: Removing OriginPoints when two straight roads are merged
|  | 10:00 - 12:30 | Niels: 2.5; Goal: Crossroad translated points
|  | 12:00 - 19:00 | David: 7; Laura: 7; Goal: fixing curved connections, crossroad arrows, saving and editing vehiclestats & driverstats
|  | 14:00 - 16:00 | Elio: 2; Niels: 2; Goal: Fix Signs hitbox + location of signs
|  | 16:00 - 16:45 | Daan: 0.75; Goal: road connection Originpoints bug
|  | 16:30 - 17:30 | Elio: 1; Goal: Fixed bug in signs + Merge GPS and Signs
|  | 18:00 - 20:00 | Marc: 4; Goal: promotional materials and minor fixes
|  | 21:00 - 22:00 | Laura: 1; Goal: Fix firstclick selected deselectable bug, make valid secondpointclick visable, Json Crossroadcontroller and gridheight
|  | 20:30 - 22:15 | Daan: 1.75; Goal: road connection Originpoints bug (almost solved...)
za | 2021-01-23 | 11:15 - 12:15 | Ravan: 1; Niels: 1; Goal: CrossRoad Connection
|  | 09:10 - 13:25 | Daan: 4.25; Elio: 4.25; Goal: road connection Origin points bug + Dijkstra
|  | 13:25 - 16:25 | Elio: 3; Goal: GPS + Dijkstra
|  | 16:25 - 17:25 | Elio: 1; Goal: Fix Signs hitbox op road
|  | 17:00 - 18:00 | Daan: 1; Goal: Testen GPS & Main
|  | 14:30 - 19:30 | Ravan: 5; Goal: CrossRoad Connection
|  | 14:00 - 15:30 | David: 1.5; Goal: Researching graph and charts
|  | 19:00 - 22:00 | Danny: 3; Goal: Hitbox Overlap
|  | 18:00 - 20:00 | David: 2; Goal: Starting with Graphs & charts
zo | 2021-01-24 | 00:30 - 02:30 | David: 2; Goal: Giving Charts live update
|  | 10:00 - 13:30 | Laura: 3.5; Goal: LaneDirection AutoSwitch
|  | 13:30 - 16:15 | David: 2.75; Laura: 2.75; Goal: AI values& graphs screen
|  | 13:45 - 16:15 | Danny: 2.5
|  | 12:00 - 17:00 | Marc: 5; Goal: Cleanup en settingscreen
|  | 11:30 - 19:00 | Ravan: 7.5; Niels: 5.5; Goal: CrossRoad connection diagonals
|  | 20:00 - 22:30 | Niels: 2.5; Goal: CrossRoad connection diagonals + merge
|  | 20:00 - 21:30 | Laura: 1.5; Goal: Clean-Up
Total week 8 |  |  | 33.25 | 30 | 12.25 | 36.25 | 34.25 | 37 | 20.25 | 34 |  | 29.6562
ma | 2021-01-25 | 11:00 - 11:30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Sprint meeting
|  | 09:00 - 11:00 | Marc: 2; Goal: Grid + settingscreeen
|  | 11:30 - 12:00 | Ravan: 0.5; Niels: 0.5; Goal: multiple lanes cross connections
|  | 12:00 - 14:00 | Marc: 2; Goal: settingscreen
|  | 11:30 - 14:30 | Danny: 3; Laura: 3; Goal: Hit box collision works
|  | 15:00 - 17:00 | David: 2; Laura: 2; Goal: AI read signs
|  | 15:00 - 19:30 | Ravan: 4.5; Goal: CrossConnections done & DrivingLane.Flippoints
|  | 17:30 - 02:00 | David: 8.5; Laura: 8.5; Goal: New Lanebased GPS
|  | 19:30 - 21:00 | Danny: 1.5; Goal: Settingscreen Signs
|  | 11:30 - 18:00 | Daan: 6.5; Elio: 6.5; Goal: Oude GPS + Start simulatie
di | 2021-01-26 | 10:00 - 11:00 | Laura: 1; Goal: Forcedlanes before crossroad
|  | 11:00 - 11:30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Extra meeting
|  | 11:30 - 12:30 | Laura: 1; Goal: Multiple possible forcedlanes
|  | 12:30 - 13:00 | Danny: 0.5; Laura: 0.5; Goal: Hitboxcollide lag fix
|  | 13:00 - 18:45 | David: 5.75; Laura: 5.75; Goal: GPS, crossroadrules AI
|  | 16:15 - 17:15 | Daan: 1; Goal: Final presentations preparations
|  | 11:30 - 17:30 | Danny: 6; Goal: Hitbox overlap, speedsign
|  | 11:30 - 18:00 | Ravan: 6.5; Niels: 6.5; Goal: Connection bug fixing (almost done)
|  | 17:00 - 20:00 | Daan: 3; Elio: 3; Goal: Final presentations preparations
|  | 21:00 - 22:45 | Daan: 1.75; Goal: Final presentations preparations
|  | 19:30 - 04:30 | David: 9; Laura: 9; Goal: GPS, AI RULES, Various fixes, Graphs
|  | 19:00 - 03:00 | Ravan: 8; Marc: 8; Niels: 8; Goal: Connections, Crossroad visualisation, signs and buttons
| 2021-01-27 | 06:00 - 09:00 | Daan: 3; Elio: 3; Goal: Final presentations preparations
|  | 09:00 - 13:00 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Final presentations
|  | 13:00 - 14:00 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Meeting
|  | 14:00 - 17:45 | Danny: 3.45; Goal: Speedsign fix, cleanup usercontrols
|  | 14:00 - 18:00 | David: 4; Goal: Added Simulation speed slider/ Fixed charts / occurunce
|  | 14:00 - 18:00 | Elio: 4; Niels: 4; Goal: Signs flip traffic light
|  | 14:00 - 18:30 | Ravan: 4.5; Goal: Bugfixing in connections
|  | 14:00 - 19:30 | Laura: 5.5; Goal: Crossroad visualisation settingsscreen, one road simulation
|  | 16:00 - 19:00 | Marc: 3; Goal: User manual
|  | 18:15 - 20:15 | Danny: 2; Goal: Usercontrols documentation and cleanup
|  | 18:00 - 20:15 | Elio: 2.25; Niels: 2.25; Goal: Traffic lights
|  | 18:30 - 20:30 | Ravan: 2; Goal: Settingscreen Crossroads
|  | 23:00 - 24:00 | Danny: 1; Goal: start to hitbox overlap fix
|  | 19:00 - 22:00 | David: 3; Goal: reworking the crossroad rules
| 2021-01-28 | 13:30 - 17:00 | Ravan: 3.5; Goal: Old Code & Controllers cleanup & documentation
|  | 12:30 - 16:30 | Danny: 4; Goal: Hitbox overlap fix
|  | 10:45 - 17:00 | Laura: 6.25; Goal: Cars can spawn on all spawnpoints and on all spawnlanes, Bugfixes, Vehicle speed fix.
|  | 15:00 - 17:00 | David: 2; Goal: improved on the intersection rules
|  | 06:45 - 19:00 | Elio: 12.25; Goal: Vehicle speed fix + other vehicle fixes + documentation & cleanup + traffic light
|  | 10:00 - 17:00 | Niels: 7; Goal: hitbox and location of signs fixed and looked at vehicle speed fix
|  | 19:00 - 20:00 | Ravan: 1; Goal: Cleanup & Documentation
|  | 23:30 - 01:00 | Danny: 1.5; Goal: Hitbox overlap and documentation
|  | 22:00 - 03:00 | Laura: 5; Goal: vehicle going back on crossroad they just left fix (pathfinding)
| 2021-01-29 | 07:30 - 10:00 | Daan: 2.5; Elio: 2.5; Goal: Bugfix signs/drivinglane buttons & Traffic lights
|  | 10:00 - 10:15 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | Last meeting with coach
|  | 10:30 - 14:15 | Ravan: 3.75; Niels: 3.75; Goal: SavePaths, SignHitbox & Lanepoints
|  | 10:15 - 13:00 | Daan: 2.75; Elio: 2.75; Goal: Traffic lights
|  | 10:45 - 14:45 | Laura: 4; Goal: GPS Comments & CleanUp
|  | 15:45 - 17:00 | Daan: 1.25; Goal: Conclusion final report
|  | 15:00 - 18:30 | Laura: 3.5; Goal: Clean-up, small fixes, code documentation research
|  | 12:30 - 19:30 | David: 7
|  | 17:00 - 22:00 | Ravan: 5; Goal: Clean-up, commenting, traffic lights and final report
|  | 13:00 - 22:00 | Elio: 9; Goal: Comments, traffic lights (old), bugfixes, cleanup and final report
|  | 19:30 - 22:00 | Laura: 2.5
|  | 18:00 - 22:00 | Marc: 4; Goal: Clean-up
|  | 14:00 - 21:30 | Niels: 7.5; Goal: Clean-up
|  | 13:00 - 14:00 | Danny: 1; Goal: Grid comments, driver profile popup
|  | 20:00 - 21:00 | David: 1; Goal: Clean-up
|  | 20:00 - 22:00 | Daan: 2; Goal: Final report
Total week 9 |  |  | 45.5 | 30 | 30.2 | 48.5 | 51.5 | 63.75 | 25.25 | 45.75 |  | 42.5562
Total |  |  | 171 | 115 | 127.7 | 205.25 | 164.5 | 255.75 | 148.5 | 190 |  | 172.2125
Needed hours |  |  | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 |  | 180
Shortage / overhours |  |  | -9 | -65 | -52.3 | 25.25 | -15.5 | 75.75 | -31.5 | 10 |  | -7.7875